## Sheet1
Activity ID | Activity Name | Duration (Days) | Start Date | End Date | Predecessors | Resources Assigned | Cost (ZAR) | Responsibility | Milestone
1 | Project Initiation | 5 | 2024-01-10 | 2024-05-10 | None | Project Manager | 50000 | Mendes
2 | Requirements Gathering | 10 | 2024-06-10 | 16/10/2024 | 1 | Business Analyst | 100000 | Philadephia
3 | Stakeholder Meetings | 3 | 2024-06-10 | 2024-08-10 | 2 | Stakeholder Group | 20000 | Philadephia
4 | Define Project Scope | 2 | 2024-09-10 | 2024-10-10 | 3 | Project Manager | 10000 | Mendes
5 | System Architecture Design | 15 | 17/10/2024 | 2024-01-11 | 4 | Systems Architect | 150000 | Philadephia
6 | Technical Specification Documentation | 5 | 2024-02-11 | 2024-06-11 | 5 | Documentation Team | 30000 | Philadephia
7 | Milestone 1: Requirements & Design Completion | 0 | 2024-01-11 | 2024-01-11 | 6 | - | - | - | Milestone 1: Requirements & Design Completion
8 | Backend Development | 20 | 2024-07-11 | 27/11/2024 | 6 | Developer Team | 400000 | Mendes
9 | Frontend Development | 15 | 2024-07-11 | 21/11/2024 | 6 | Designer | 200000 | Bulisile
10 | User Interface Design | 10 | 22/11/2024 | 2024-02-12 | 9 | Designer | 100000 | Bulisile
11 | API Integration | 10 | 22/11/2024 | 2024-02-12 | 8 | Developer Team | 100000 | Thabo
12 | Data Parsing | 7 | 2024-03-12 | 2024-09-12 | 11 | Data Specialist | 50000 | Philadephia
13 | Develop Recommendation Algorithm | 10 | 2024-10-12 | 20/12/2024 | 12 | Data Scientist | 80000 | Mendes
14 | Implement Search Backend | 8 | 21/12/2024 | 29/12/2024 | 13 | Developer Team | 70000 | Bulisile
15 | Design Browsing UI | 7 | 30/12/2024 | 2025-06-01 | 14 | Designer | 50000 | Bulisile
16 | Implement Browsing Interface | 10 | 2025-07-01 | 17/01/2025 | 15 | Developer Team | 100000 | Thabo
17 | User Profile Creation | 5 | 18/01/2025 | 22/01/2025 | 16 | Developer Team | 50000 | Mendes
18 | Subscription Management | 5 | 23/01/2025 | 27/01/2025 | 17 | Developer Team | 50000 | Thabo
19 | Security Testing | 7 | 28/01/2025 | 2025-03-02 | 18 | QA Team | 50000 | Bulisile
20 | Milestone 2: Development and UI/UX Completion | 0 | 2025-03-02 | 2025-03-02 | 19 | - | - | - | Milestone 2: Development & UI/UX Completion
21 | Integrate Payment Gateway | 5 | 2025-04-02 | 2025-08-02 | 20 | Payment Specialist | 40000 | Mendes
22 | Conduct System Testing | 10 | 2025-09-02 | 19/02/2025 | 21 | QA Team | 100000 | Bulisile
23 | Bug Fixing and Optimization | 10 | 20/02/2025 | 2025-02-03 | 22 | Developer Team | 100000 | Mendes
24 | User Acceptance Testing | 7 | 2025-03-03 | 2025-10-03 | 23 | QA Team | 50000 | Philadephia
25 | Final Deployment | 5 | 2025-11-03 | 15/03/2025 | 24 | DevOps | 50000 | Mendes
26 | Milestone 3: Final Deployment and Launch | 0 | 15/03/2025 | 15/03/2025 | 25 | - | - | - | Milestone 3: Final Deployment & Launch
27 | Marketing Campaign Launch | 7 | 16/03/2025 | 23/03/2025 | 26 | Marketing Team | 70000 | Bulisile
28 | Social Media Advertising | 5 | 24/03/2025 | 28/03/2025 | 27 | Marketing Team | 50000 | Bulisile
29 | Customer Onboarding and Training | 7 | 29/03/2025 | 2025-05-04 | 28 | Training Team | 50000 | Philadephia
30 | Conduct Feedback Survey | 3 | 2025-06-04 | 2025-08-04 | 29 | Customer Support Team | 20000 | Bulisile
31 | Documentation and Reporting | 5 | 2025-09-04 | 13/04/2025 | 30 | Documentation Team | 30000 | Tshepo
32 | Project Closure and Sign-Off | 2 | 14/04/2025 | 15/04/2025 | 31 | Project Manager | 10000 | Mendes
33 | Post-Launch Support and Maintenance | 30 | 16/04/2025 | 15/05/2025 | 32 | Support Team | 150000 | Mendes

## Sheet2
Task Name | Start Date | Duration (Days) | End Date
Project Initiation | 2024-10-01 | 5 | 2024-10-05 | 2024-01-02
Requirements Gathering | 2024-10-06 | 10 | 2024-10-16 | 17/10/2024
Stakeholder Meetings | 2024-10-06 | 3 | 2024-10-08
Define Project Scope | 2024-10-09 | 2 | 2024-10-10
System Architecture Design | 2024-10-17 | 15 | 2024-11-01
Technical Specification Documentation | 2024-11-02 | 5 | 2024-11-06
Backend Development | 2024-11-07 | 20 | 2024-11-27
Frontend Development | 2024-11-07 | 15 | 2024-11-21
User Interface Design | 2024-11-22 | 10 | 2024-12-02
API Integration | 2024-11-22 | 10 | 2024-12-02
Data Parsing | 2024-12-03 | 7 | 2024-12-09
Develop Recommendation Algorithm | 2024-12-10 | 10 | 2024-12-20
Implement Search Backend | 2024-12-21 | 8 | 2024-12-29
Design Browsing UI | 2024-12-30 | 7 | 2025-01-06
Implement Browsing Interface | 2025-01-07 | 10 | 2025-01-17
User Profile Creation | 2025-01-18 | 5 | 2025-01-22
Subscription Management | 2025-01-23 | 5 | 2025-01-27
Security Testing | 2025-01-28 | 7 | 2025-02-03
Integrate Payment Gateway | 2025-02-04 | 5 | 2025-02-08
Conduct System Testing | 2025-02-09 | 10 | 2025-02-19
Bug Fixing and Optimization | 2025-02-20 | 10 | 2025-03-02
User Acceptance Testing | 2025-03-03 | 7 | 2025-03-10
Final Deployment | 2025-03-11 | 5 | 2025-03-15
Marketing Campaign Launch | 2025-03-16 | 7 | 2025-03-23
Social Media Advertising | 2025-03-24 | 5 | 2025-03-28
Customer Onboarding and Training | 2025-03-29 | 7 | 2025-04-05
Conduct Feedback Survey | 2025-04-06 | 3 | 2025-04-08
Documentation and Reporting | 2025-04-09 | 5 | 2025-04-13
Project Closure and Sign-Off | 2025-04-14 | 2 | 2025-04-15
Post-Launch Support and Maintenance | 2025-04-16 | 30 | 2025-05-15